## Tasks
Table 1
Task No. | Subtask | Assigned To | Start Date | Deadline | Notes
1.1 | Data Understanding | Stefany, Chris | 10-May | 12-May | Explore dataset, handle missing values/duplicates
1.2 | Data Visualization | Samy, Favour | 10-May | 13-May | Create histograms, correlation matrices (can work parallel with 1.1)
2.1 | Feature Selection | Beyza, Hendrik | 13-May | 15-May | Identify relevant features, feature engineering
2.2 | Data Preprocessing | Samy, Chris | 14-May | 16-May | Handle categorical variables (can start after 1.2 finishes)
3.1 | Model Options | Stefany, Hendrik | 15-May | 16-May | Define problem, evaluate model options
3.2 | Model Justification | Favour, Beyza | 16-May | 17-May | Final model choice, define metrics
4.1 | Model Training | Stefany, Samy | 17-May | 18-May AM | Train model, hyperparameter tuning
4.2 | Cross-Validation | Hendrik, Favour | 17-May | 18-May AM | Assess performance (can run parallel with 4.1)
5.1 | Final Evaluation | Chris, Beyza | 18-May PM | 18-May PM | Test evaluation
5.2 | Lessons Learned | Favour, Stefany | 18-May PM | 18-May PM | Document challenges
- | Presentation Prep | All | 18-May PM | 18-May EOD | Consolidate findings for presentation

## Gantt Chart
Table 1
Task | Assigned To | Start Date | End Date | Duration (Days) | May 10 | May 11 | May 12 | May 13 | May 14 | May 15 | May 16 | May 17 | May 18
Data Understanding | Stefany, Chris | 10-May | 12-May | 3 | May 10: █████; May 11: █████; May 12: █████
Data Visualization | Samy, Favour | 10-May | 13-May | 4 | May 10: █████; May 11: █████; May 12: █████; May 13: █████
Feature Selection | Beyza, Hendrik | 13-May | 15-May | 3 | May 13: █████; May 14: █████; May 15: █████
Data Preprocessing | Samy, Chris | 14-May | 16-May | 3 | May 14: █████; May 15: █████; May 16: █████
Model Options | Stefany, Hendrik | 15-May | 16-May | 2 | May 15: █████; May 16: █████
Model Justification | Favour, Beyza | 16-May | 17-May | 2 | May 16: █████; May 17: █████
Model Training | Stefany, Samy | 17-May | 18-May AM | 1.5 | May 17: █████; May 18: ███
Cross-Validation | Hendrik, Favour | 17-May | 18-May AM | 1.5 | May 17: █████; May 18: ███
Final Evaluation | Chris, Beyza | 18-May PM | 18-May PM | 0.5 | bar: May 18
Presentation Prep | All | 18-May PM | 18-May EOD | 0.5 | bar: May 18